## Estimate(USD)
Phase | Platform | Module | Sub-function | Comment |  | Estimate
[5 empty] | PM/BA | Dev | UI | QA
MVP |  |  | DataBase design |  | 2 | 4
MVP |  |  | Requirement Analysis |  | 4 | 4 |  | 4
MVP |  |  | Prototype and UI design |  | 5 |  | 5
Phase II |  |  | DataBase design |  | 3 | 5
Phase II |  |  | Requirement Analysis |  | 5 | 5 |  | 4
Phase II |  |  | Prototype and UI design |  | 10 |  | 10
MVP | YOLAD Platform | Login/Logout | Login/Logout/Forgot password |  | 1 | 2 |  | 2
MVP |  | Accounts Management | Create/delete/modify accounts/Roles/Permission |  | 1 | 4 |  | 3
MVP |  | Clients Management | active/inactive/modify accounts | basic information only | 1 | 6 |  | 3
MVP |  | SKILLAS Management | active/inactive/modify accounts | basic information only | 1 | 8 |  | 3
MVP |  | Jobs Management | List/details | basic information only | 1 | 6 |  | 3
MVP |  | Skills Management | List | basic information only | 1 | 4 |  | 1
MVP |  | Courses Management | List/details | Video files only | 1 | 6 |  | 3
Phase II |  | Orders Management | List/Detail | Course Orders only | 2 | 10 |  | 6
Phase II |  | Payments Management | List/Detail/transfer/refund | Credit Card and Paypal | 5 | 30 |  | 6
Phase II |  | Financials Management | Report | Income，refund report | 2 | 10 |  | 2
Phase II |  | Audit | Access log，Api Log, Change Log | just save data without page | 1 | 5 |  | 2
Phase II |  | System Settings | Payment Gate, mail, IM |  | 2 | 10 |  | 5
MVP | Client Platform | Login/Logout | Login/Logout/Forgot password |  | 1 | 1 |  | 1
MVP |  | Jobs Management | create/publish | Basic information | 2 | 10 |  | 4
Phase II |  | Payments Management | List/Detail | Pay to YOLAD only via Credit Card and Paypal | 4 | 15 |  | 6
Phase II |  | Financials Management | Report | expense report | 1 | 3 |  | 3
MVP | Training Institution Platform | Login/Logout | Login/Logout/Forgot password |  | 1 | 1 |  | 1
MVP |  | Courses Management | create/publish | Basic Course information and Upload video files only | 1 | 10 |  | 2
Phase II |  | Orders Management | List/Detail |  | 2 | 20 |  | 3
Phase II |  | Payments Management | List/Detail/transfer/refund | Credit Card and Paypal | 2 | 15
Phase II |  | Financials Management | Report | Income，expense, refund report | 1 | 15 |  | 2
MVP | SKILLAS Platform | Login/Logout | Login/Logout/Forgot password |  | 1 | 1 |  | 1
MVP |  | Jobs List | Matched or All Jobs list | matching skills | 1 | 6 |  | 2
MVP |  | Courses List | Matched or All Courses list | matching courses' tag | 1 | 6 |  | 2
MVP |  | My job | Applied Job | List and details | 1 | 5 |  | 2
MVP |  | My Training | Bought Courses | List and details, Play video | 1 | 5 |  | 1
MVP |  | Profiles |  | Basic information | 1 | 5 |  | 1
Phase II |  | Payment |  | Pay to YOLAD only via Credit Card and Paypal, and order history | 2 | 15 |  | 1
MVP | Web Platform | Static Web Pages |  | About, Contact , Company ,Career , Partner and Resource pages only | 2 | 6 |  | 1

## General tasks durations
skills | duration(days)
Skill creating and display | 12
custom quotes | 7
editing skills and delete | 3
payment integration | 7
admin panel | 24
history page | 3
modification of pages | 14

## Estimate (GBP)
Phase | Platform | Module | Sub-function | Comment |  | Estimate
[5 empty] | PM/BA | Dev | UI | QA
MVP |  |  | DataBase design |  | 2 | 4
MVP |  |  | Requirement Analysis |  | 4 | 4 |  | 4
MVP |  |  | Prototype and UI design |  | 5 |  | 5
Phase II |  |  | DataBase design |  | 3 | 5
Phase II |  |  | Requirement Analysis |  | 5 | 5 |  | 4
Phase II |  |  | Prototype and UI design |  | 10 |  | 10
MVP | YOLAD Platform | Login/Logout | Login/Logout/Forgot password |  | 1 | 2 |  | 2
MVP |  | Accounts Management | Create/delete/modify accounts/Roles/Permission |  | 1 | 4 |  | 3
MVP |  | Clients Management | active/inactive/modify accounts | basic information only | 1 | 6 |  | 3
MVP |  | SKILLAS Management | active/inactive/modify accounts | basic information only | 1 | 8 |  | 3
MVP |  | Jobs Management | List/details | basic information only | 1 | 6 |  | 3
MVP |  | Skills Management | List | basic information only | 1 | 4 |  | 1
MVP |  | Courses Management | List/details | Video files only | 1 | 6 |  | 3
Phase II |  | Orders Management | List/Detail | Course Orders only | 2 | 10 |  | 6
Phase II |  | Payments Management | List/Detail/transfer/refund | Credit Card and Paypal | 5 | 30 |  | 6
Phase II |  | Financials Management | Report | Income，refund report | 2 | 10 |  | 2
Phase II |  | Audit | Access log，Api Log, Change Log | just save data without page | 1 | 5 |  | 2
Phase II |  | System Settings | Payment Gate, mail, IM |  | 2 | 10 |  | 5
MVP | Client Platform | Login/Logout | Login/Logout/Forgot password |  | 1 | 1 |  | 1
MVP |  | Jobs Management | create/publish | Basic information | 2 | 10 |  | 4
Phase II |  | Payments Management | List/Detail | Pay to YOLAD only via Credit Card and Paypal | 4 | 15 |  | 6
Phase II |  | Financials Management | Report | expense report | 1 | 3 |  | 3
MVP | Training Institution Platform | Login/Logout | Login/Logout/Forgot password |  | 1 | 1 |  | 1
MVP |  | Courses Management | create/publish | Basic Course information and Upload video files only | 1 | 10 |  | 2
Phase II |  | Orders Management | List/Detail |  | 2 | 20 |  | 3
Phase II |  | Payments Management | List/Detail/transfer/refund | Credit Card and Paypal | 2 | 15 |  |  |  | 73 | 258 | 15 | 80
Phase II |  | Financials Management | Report | Income，expense, refund report | 1 | 15 |  | 2
MVP | SKILLAS Platform | Login/Logout | Login/Logout/Forgot password |  | 1 | 1 |  | 1 | Total | 426
MVP |  | Jobs List | Matched or All Jobs list | matching skills | 1 | 6 |  | 2
MVP |  | Courses List | Matched or All Courses list | matching courses' tag | 1 | 6 |  | 2
MVP |  | My job | Applied Job | List and details | 1 | 5 |  | 2
MVP |  | My Training | Bought Courses | List and details, Play video | 1 | 5 |  | 1 | MVP | 31 | 100 | 10 | 40
MVP |  | Profiles |  | Basic information | 1 | 5 |  | 1 | MVP Total | 181
Phase II |  | Payment |  | Pay to YOLAD only via Credit Card and Paypal, and order history | 2 | 15 |  | 1 |  | 47784
MVP | Web Platform | Static Web Pages |  | About, Contact , Company ,Career , Partner and Resource pages only | 2 | 6 |  | 1
MVP |  | Workload |  |  | 181
|  | Estimate |  |  | 47784
Total |  | Workload |  |  | 426
|  | Estimate |  |  | 112464